## Risk Management Plan 2020
Risk Area | Specific Concern | Risk | Impact | Likelihood | Internal Control | Agreed improvements 2020 | Who | Target Date | Review Date(s) & Comment
Assets | IT Equipment | Theft, damage or loss to IT equipment used by Parish Clerk | L | L | Insurance covers cost of replacement; Equipment kept in locked office at home of Clerk; . | Reclaim Apple Mac in storage at Tearooms (delayed because of Covid-19). | Parish Clerk Cllr Sinclair | Quarter 3
Assets | Playground | Risk of injury or death to young person using defective, faulty, slippery or poorly maintained playground equipment, seating or picnic tables; Risk of damage making playground unusable | H | L | Playground equipment recently renewed (2019); insurance cover; Inspect all playground and amusement devises at least every seven days. Third party RoSPA audit annually. Any damage or defect must be rectified as soon as possible. Defective equipment which is a risk to health and safety taken out of use immediately and repaired as soon as possible, regular programme of grass cutting. | Weekly and monthly checks documented and saved on the One Drive. | Cllr Cross Cllr Millward | Weekly Monthly Annually
Assets | Playing Fields | Risk of injury from poorly maintained playing fields. Damage caused by users of the space. Area no longer secure due to failure of fencing (see also Trees) | H | M | Leases devolve responsibility to regular users of playing fields (Tennis Club, Sports Pavilion). Regular grass cutting by contractor. Dog mess bins. | Include in weekly and monthly checks of playground. Check leases for devolved responsibilities to users of the clubs. Review signage and waste bins on playing fields. | Cllr Cross Cllr Millward | Quarter 3
Assets | Seating | Risk of injury if poorly maintained/ damaged/ vandalised | L | L |  | Identify all seating and include in Annual Infrastructure Audit | Cllr Littlewood Cllr Tongue | Quarter 3
Assets | Grit Bins | Unusable if poorly maintained therefore inadequately prepared for bad weather | L | L |  | Identify all grit bins and include in Annual Infrastructure Audit | Cllr Littlewood Cllr Tongue | Quarter 3
Assets | Trees | Risk of injury or death to person if unsafe; Risk of damage to property | H | L | Tree Survey completed Dec 2018 identified trees for immediate action and action within 12m. | 6-monthly checks, documented. Check have all actions from 2018 Tree Survey been completed? Budget for new Tree Survey in 2021. | Cllr Sinclair Cllr Bardsey | Quarter 3, Quarter 1 2021
Assets | Street Lighting | Street Lighting failure/ interruption of power supply | L | L | Electricity charges paid by standing order. Programme of replacement underway; Annual Direct Debit set-up; | Street lighting upgrade underway by WCC; Identify all lighting and Include visual check in Annual Infrastructure Audit. | Cllr Millward Cllr Cross | 01/03/2020 31/3/2021 | Annual Direct Debit confirmed set-up for 2020-21
Assets | Breech Furlong | Tenant breaches terms of lease; Brings TPC into disrepute, | L | L | Professionally drawn up lease, recently renewed | Review renewal date for Lease. | Parish Clerk | Quarter 3
Assets | Bus Shelter | Risk of injury if poorly maintained/ damaged/ vandalised | L | L |  | Include visual check in Annual Infrastructure Audit | Cllr Cross | Quarter 3
Assets | Village Green & Verges | Damage to village green and verges widening the roads and encroaching on footpaths presenting risk to residents. | L | M | Prompt reporting of any problems to WCC/Highways and/or Police | Proactive communications to School, Contractors and Residents; Create policy documenting approach by PC. Schedule of presenting parking notices; Installation of wooden bollards to protect verge where appropriate | Cllr Cross Cllr Littlewood Cllr Tongue | Quarter 3
Employment | HMRC | Comply with Inland Revenue requirements | L | L | Professional payroll services employed. Internal and external auditor carry out annual checks. BACS payments agreed as Regular Payment. | Retain contract with Payroll Services. Request copy of Professional Indemnity Insurance certificate | Parish Clerk | 2020-03-01 | DM Payroll retained.
Employment | Employer Liability | Comply with Employment Law | L | L | Council members keep up to date via WALC/NALC; Employer Liability Insurance | NONE | Cllr Cross Cllr Millward
Employment | Health & Safety | Safety of staff - risk of injury whilst conducting role | L | L | Employer Liability insurance | Parish Clerk to complete DSE check for home working | Parish Clerk | Quarter 3
Finance | Banking collapse | Inability to provide services due to loss of funds due to bank collapse, theft, fraud, or other loss | H | L | Accounts held with at reputable high street bank, deposits with bank do not exceed £85,000 - the current level for protection under the Financial Services Compensation Scheme | NONE | Cllr Sinclair Cllr Millward
Finance | Budgeting | Budgeting process not robust and Precept does not meet requirements. Service is not adequate for residents. | M | L | Council receive detailed budgets in the late autumn. Precept derived directly from this (detailed in Financial Regs 2020). Expenditure against budget reported and monitored monthly. Budget for one year's Precept in Reserves. | Annual Parish Assembly to inform budgeting process | All Members | May 2020 revisited in September 2020 | May Parish Assembly postponed due to Covid-19 pandemic.
Finance | Controls | Inability to provide services due to loss of funds due to poor financial controls. | M | L | Financial Regulations reviewed and updated May 2020. Monthly Finance Pack including bank reconciliation prepared by Clerk/RFO and reported to Council. Cllr Millward actioning all payments via internet banking; Two signatories on cheques. Internal and external audit. Internet banking payments of £1000+ trigger alerts to Chairman and Deputy. All payments over £3000 are paid by cheque (two signatories required). Daily banking limit is £3000. | Investigate dual signatory account (Unity Bank) for internet banking | Parish Clerk | Quarter 3
Finance | HMRC | Risk of financial penalty, prosecution and/or loss of income caused by inaccurate, false VAT claims. | M | L | Use help line when necessary. VAT payments and claims calculated by Scribe and checked by Clerk. Internal and external auditor to provide double check. | NONE | Parish Clerk
Finance | Borrowing | Poor borrowing decisions lead to financial loss. | M | L | No new borrowing planned. | NONE | Cllr Sinclair Cllr Millward
Finance | Cash | Loss of cash through theft or dishonesty | M | L | No cash held | NONE | Cllr Sinclair Cllr Millward
Finance | Debtors | Funds not repayed | L | L | Monthly review of outstanding debtors | NONE | Parish Clerk Cllr Sinclair Cllr Millward
Finance | Suppliers | Loss of funds if Suppliers do not provide contracted services. | L | L | Reputable contractors used. Previous working relationships. References provided. Not paid until works complete | Tender process to be conducted annually in October to inform budget process and in readiness for new financial year | Parish Clerk | Quarter 3
Finance | Grants from TPC | Funding awards not used for intended purposes | L | L | Grants Policy agreed through resolution of Council | Review and update Grants Policy. | Parish Clerk All Members | Quarter 3
Finance | Grants to TPC | Funding misspent and return requested by grant giver | L | L | s106 Funding ringfenced in Scribe and reported on separately. Spend agreed through resolution of Council. | NONE | Parish Clerk Cllrs Sinclair & Millward
Infrastructure | Flooding | Risk to property and life | L | M | Report blocked drains to WCC, access to gel sandbags. | Promote contact lists to residents to ensure awareness if emergencies to arise. Include visual check of water courses, drains, culverts and mesh, in Annual Infrastructure Audit | Cllr Littlewood Cllr Tongue | Quarter 3
Infrastructure | Rights of Way (Footpaths/ Bridle paths) | Become impassable. Residents injure themselves clearing the path. Residents injure themselves slipping on overgrown vegetation | L | L | WCC maintain most footpaths, promote website reporting, some regular maintenance carried out (Oxhill Road – The Manor, Poolgate to Baldwins Lane) but no consistent approach. | Annual review of footpaths in area. Ask WCC when they will come to check the footpaths? Consider need for Emergency/Contingency Plan | All Members Parish Clerk | Quarter 3
Insurance | Insurance | Inadequate insurance for loss incurred. Insurance does not pay out. | H | L | Reputable, established insurer | Annual Review (3 quotes) | Parish Clerk | Quarter 4
Legal | Legal Liability | Due process not followed when calling meetings, minutes do not adequately reflect the meeting, minutes are not available within the timescales required. | L | L | Council meets once a month and receives and approves Minutes before posting within timescales. Minutes are made available to public on the Noticeboard and via the web site. | NONE
Legal | Document Control | Proper document control | M | L | Leases and legal documents stored with Clerk for reference and safe storage. | Check all leases and legal documents present and complete. | Parish Clerk | Quarter 3
Legal | Data Loss | Loss of documentation due to fire or negligence | M | L | Data is stored and backed up on Parish Clerk’s laptop and memory drive. Meeting minutes and agendas are saved to the Parish website; Printouts of papers retained by Parish Clerk for 2 years and then stored in Village Hall. Automatic Hourly back-up to secure medium to ensure integrity of data, records and GDPR related information | Contact WCC to investigate archiving of past Parish Council documentation. Update usernames and passwords to be printed and secured by Chairman. Investigate Norton 360 et al for safer storage of data. | Parish Clerk | Quarter 3
Legal | Public Liability | Risk to third party, property or individuals | H | L | Public Liability insurance in place. See individual Assets | NONE
Legal | Data Protection | Loss of subject data | H | L | Data Retention Policy; Parish Council email addresses for all parties | Review Data Retention Policy; comply with Data Retention Policy Schedule | Parish Clerk All Members | Quarter 3
Legal | Legal Powers | Activities are not within legal powers | M | M | Clerk clarifies legal position on any new proposal. Legal advice to be sought from WALC/NALC where necessary. | Legal powers used to be referenced in minutes. | Parish Clerk | On-going

## Sheet3
Impact | Likelihood
L | L
M | M
H | H